3D Mezzanine Model, Handoff Plan to TUUCI

Prepared 07/14/2026 · Updated 07/16/2026 · Mac O'Keefe, Continuous Improvement · DRAFT for review with Engineering + IT

1 · What TUUCI is receiving

3D Mezzanine Model: the whole mezzanine (Meritage, Sola, Canyon Crew) animated with live cycle/pace/capacity/bottleneck math, per-product standard work, product-specific help paths, crew coverage rules, a daily Planner, a Takt board with a help-path optimizer, and a toolbar that separates daily analysis tools from floor-editing tools. Any browser, no install. TUUCI-branded copy included.

Source code: one JavaScript source plus a one-command build and the TUUCI theming script.

Data & assumptions register: every measured SWI, which numbers are measured vs estimated, and the model assumptions.

Related docs: Meritage connector ECN and PCN drafts, improvement presentation, meeting deck.

2 · The end state (what "handed off" means)

Two roles, one shared source of truth:

Admin page (Engineering/CI): the back end and workflow design. Stations, step times, products, coverage rules, floor layout, cart routes. Maps to the app’s "Floor tools" + Edit times side today.

Floor manager page (line supervisors, daily): what each line builds today, how many, in what order, with how many people; the tool returns the schedule, the takt picture, and the best help-path setup. Maps to the Planner + Takt board side today.

Shared data in TUUCI’s Microsoft 365: one person saves, everyone sees it on next load. No forked copies.

The current app already previews this split (daily tools visible, floor tools behind a toggle). The handoff makes it real with storage, permissions, and owners.

3 · Where the data should live (verified)

The Microsoft 365 TUUCI already pays for; no new server. The store is a SharePoint List, one row per saved layout, on a shared SharePoint/Teams site, read and written through the Microsoft Graph API with each person’s normal M365 sign-in.

Why a List and not a shared file on OneDrive: two near-simultaneous saves to a file produce a silent conflict copy and one person’s edits disappear. A List gives per-layout collisions only, rejection of stale saves (the app re-loads and warns instead of overwriting), and per-item version history: who changed what, when.

Hosting: The app page is served from a static web address (internal web server, Azure Static Web Apps, or SharePoint SPFx). SharePoint hands a raw .html back as a download, so the page cannot live in the folder itself. Static hosting, not an application server.

Admin consent: One-time Entra "SPA" app registration plus tenant admin consent for the Graph scope (Sites.ReadWrite.All). About 15 minutes, once.

The code funnels every read/write through four functions, so the localStorage-to-Graph swap is roughly one to two days of development.

Interim bridge (start now, zero IT): one official copy on the SharePoint/Teams site; one owner republishes it via "Save into app"; everyone opens from that link only. Use a Teams site, not a personal OneDrive, so nothing orphans.

4 · Roles and permissions

Admin (Engineering/CI): full app. Publishes Official layouts, times, products, coverage rules. Official time changes require an SWI behind them and update the measured-vs-estimated register in the same change.

Floor manager: Planner, Takt board, charts, product selection, day length and crew for the day. Cannot overwrite Official layouts.

Enforcement, phased: first by convention (Floor-tools toggle / two builds), later by role check on the M365 sign-in.

5 · Handoff phases

| Phase | What happens | Who | Effort |
| --- | --- | --- | --- |
| 0. Now | Publish the official copy to the SharePoint/Teams site ("open from here only"); tag a v1 of the repo; list known assumptions | CI | 1 hr |
| 1. Storage | IT setup (site, Layouts list, Entra SPA registration, admin consent); implement MSAL + Graph in the four storage functions; host on an internal HTTPS URL | CI + IT | 2-3 days |
| 2. Pilot | 2-3 users run it for a week; verify saves propagate, nothing lost, numbers trusted | CI | 1 week parallel |
| 3. Roles | Split admin vs floor-manager experience; train supervisors on Planner/Takt board only | CI + IT | 2-3 days |
| 4. Ownership | Name technical owner and data owner; move repo into TUUCI’s org; training (1 hr supervisors, 2 hr admin) + cheat sheets | Mgmt + CI | 1/2 day + sessions |
| 5. Support | Issues route to the data owner; assumptions register stays current; keep grounding times in real SWIs | Data owner | ongoing |

6 · Definition of done

Data lives in the shared M365 store; a two-person concurrent-save test passes.

Every official step time is SWI-measured or explicitly flagged as an estimate.

Named technical owner and data owner have accepted the roles.

Supervisors can run a day’s plan in the Planner without help.

Repo, build instructions, and theming script live in a TUUCI-controlled repository.

7 · Open decisions for TUUCI

App hosting: internal web server vs Azure Static Web Apps vs SharePoint (SPFx).

Who performs the Entra app registration and admin consent.

Backup/retention of the Layouts list beyond version history.

Named technical owner and data owner.

Whether the TUUCI-branded skin becomes the primary look (recommended).